YɛnCare Health Platform

Master Sprint Plan & Forward Task Allocation: Week 3 (Gate 3 Feature-Complete & Strict Freeze)

| Programme / Context | AmaliTech CSR Capstone Internship Programme — Product 4 (KNUST Health Services) |
| --- | --- |
| Active Sprint State | Week 2 (Gate 2) 100% COMPLETE & VERIFIED • Week 3 Active Sprint Initiated (9 Tasks) |
| Current Execution Date | Thursday, 10 September 2026 (Gate 2 Sign-off — Week 3 Kickoff) |
| Milestone Objective | Deliver all operational and self-service features (cancellations, virtual queue tracking, doctor consultation workflow, walk-in triage, call-next SMS) to reach complete functional scope by Friday, 18 September 2026, 5:00 PM Feature Freeze. |
| Lead Author & Role | Blessing Edmund Kwame Dogbe (Backend & DevOps Lead / Product Coordinator) |

# 1. Team Roster & Competency Allocation

Tasks across all milestones are assigned strictly according to team members' demonstrated engineering strengths, previous milestone performance, and architectural requirements for Gate 3:

| Team Member | Discipline / Focus | Demonstrated Strengths | Week 3 Active Focus |
| --- | --- | --- | --- |
| Blessing Edmund Kwame Dogbe | DevOps / Backend Lead | Multi-provider SMS gateway (mNotify/AT), GitHub Actions CI pipelines, Render staging orchestration, release governance. | Staging environment autoscaling, Atlas database backups, Gate 3 verification & final submission. |
| Able Kafu Azanda | Backend Lead Architect | MongoDB Mongoose schema design, compound indexing, double-booking prevention guards, transactional slot locking, test suites. | Virtual queue engine & token state machine, atomic cancellation & slot release API. |
| Emmanuella Lodonu | Backend Foundations | Express REST APIs, patient registration & lookup (`/api/patients`), input normalization, transactional SMS dispatch triggers. | Call-next patient SMS alert dispatch (`CALLED` event), staff queue operations API support. |
| Harry “Ephraim” Nartey | Fullstack Foundations | Frontend Axios HTTP client, React state management, staff operational dashboards, check-in desk workflow. | Doctor consultation room workflow (S04/S05), walk-in fast-track desk triage intake (S01/S02). |
| Raymond B. Afrani | Frontend Foundations | Responsive React component engineering, patient intake wizard (P01-P07), emergency triage gate, form validation. | Virtual queue live tracking screen (P18), self-service cancellation & reschedule UI (P11-P17). |

# 2. Updated Sprint State: Gate 2 100% Passed & Week 3 Active

As of Thursday, 10 September 2026, Gate 2 has been officially audited, tested end-to-end, and verified at 100% completion. All 12 Gate 2 cards are closed. The repository is in an exemplary state with 74/74 passing backend tests, clean production builds, working live SMS delivery, and zero lint warnings:

| Lifecycle Stage | Card Count | Percentage | Active Cards / Milestone Focus |
| --- | --- | --- | --- |
| Gate 2 Verified (Done) | 12 | 100.0% | All Gate 2 scope closed: Mongo schema, SMS gateway, Patient API, Booking API, Double-booking clash guard, UI wizard, Staff check-in. |
| Week 3 Active Sprint | 9 | In Progress | Gate 3 Feature-Complete: Virtual Queue, Cancellation API, Call-Next SMS, Doctor Consultation Room, Walk-in Triage, Staging. |
| Week 4 Hardening Backlog | 5 | Planned | Gate 4: Concurrency stress testing, security audit, mobile responsiveness, offline resilience, architecture documentation. |
| Week 5 Final Demo Backlog | 4 | Planned | Gate 5: Full clinical simulation rehearsal, throughput modeling, executive pitch deck, capstone defense. |

Official Gate 2 Verification Verdict: PASSED Gate 2 Core Milestone 100% Complete & Live-Verified! • End-to-end booking executed live on web app: Patient Kwame Mensah Gate2 booked with Dr. Kwame Boateng (Ref: YC-8166). • Live Ghana SMS dispatch confirmed via mNotify Quick SMS v2 (Credit remaining: 285). • Database double-booking clash guard implemented & verified: second booking attempt for same clinician/time slot rejected with HTTP 409 Conflict. • Staff Operations Portal (/staff) verified: today's roster loaded, live desk check-in updated booking status from BOOKED to CHECKED_IN. • Quality gates green: 74/74 backend unit tests passing, frontend production build passing (2.58s), prototype build passing (1.11s), 0 lint errors.

# 3. Completed Work Log: 12 Gate 2 Verified Tasks

All 12 deliverables committed under Gate 2 have been completed, tested against MongoDB Atlas, and merged into the main branch:

| Card Title & Prefix | Primary Owner | Verified Date | Delivered Artifacts & Technical Impact |
| --- | --- | --- | --- |
| [BE] Design MongoDB Schema & Core Models | Able Azanda | Mon, 7 Sep | Delivered Mongoose models for Patient, Appointment, Clinician, Room, TimeSlot with compound index specs. |
| [DEVOPS] Configure SMS Provider (mNotify) & Sandbox | Blessing Dogbe | Tue, 8 Sep | Integrated mNotify API v2 Quick SMS. Sender ID 'YenCare' verified; added Africa's Talking and Mock fallbacks. |
| [BE] Patient Registration & Verification API | Emmanuella Lodonu | Tue, 8 Sep | Built `POST /api/patients` and `GET /api/patients/:identifier` supporting 8-digit KNUST index and Ghana phones. |
| [FE] Landing Page & Patient Intake Wizard (P01-P02C) | Raymond Afrani | Tue, 8 Sep | Implemented Home landing, P02 Personal Details, P02B Clinic Site Selector, and P02C Visit Triage with Emergency Gate. |
| [BE] Appointment Booking API with Concurrency Lock | Able Azanda | Tue, 8 Sep | Delivered `createAppointment` service with reference code generation (`YC-XXXX`) and database transaction safety. |
| [TEST] Automated Test for Double-Booking Prevention | Able Azanda | Tue, 8 Sep | Added unit tests verifying compound unique indexes on time_slots for clinician and room. |
| [BE] Hook SMS Dispatch Trigger on Appointment Creation | Emmanuella Lodonu | Tue, 8 Sep | Integrated `sendSms` in `bookAppointment.js`. Fires transactional confirmation text upon successful MongoDB insert. |
| [FS] Set Up API Client & State Connection in React | Harry Nartey | Wed, 9 Sep | Constructed Axios API client layer (`services/api.js`, `patients.js`, `appointments.js`) with loading/error handlers. |
| [FE] Clinic Site, Clinician & Time Slot Picker (P03-P05) | Raymond Afrani | Wed, 9 Sep | Built doctor selection, multi-site filtering, and 30-minute time slot selection with 15-minute arrival guidance. |
| [FE] Booking Review & Confirmation Screen (P06-P07) | Raymond Afrani | Wed, 9 Sep | Delivered Review Booking card with live API submission, loading states, and Confirmation screen displaying `YC-XXXX`. |
| [FS] Staff Operations Dashboard & Live Check-In View | Harry Nartey | Thu, 10 Sep | Built `/staff` portal with today's roster, desk search, status filter tabs, and interactive Check-In transition. |
| [BE/FIX] Atomic Double-Booking Clash Guard & Conflict API | Able / Blessing | Thu, 10 Sep | Added active booking check in `bookAppointment.js` rejecting duplicate clinician/slot with HTTP 409 Conflict; added test. |

# 4. Week 3 Active Sprint Tasks (Gate 3 Feature-Complete — 9 Tasks)

Goal of Week 3 (14 Sep – 18 Sep 2026): Deliver all remaining operational and patient self-service features to achieve complete functional scope. A strict Feature Freeze will be enforced at 5:00 PM on Friday, 18 September 2026. Absolutely no new features will be introduced after this deadline.

| [BE] Virtual Queue Engine & Token Progression State Machine |  |
| --- | --- |
| Status & Milestone | Active — High Priority ¦ Week 3 (Gate 3 Feature-Complete) |
| Assignee & Support | Primary: Able Kafu Azanda (AA) • Support: Blessing Edmund Kwame Dogbe (Lead) |
| Assignment Rationale | Able designed the core database schema and transactional locking; he is best equipped to implement deterministic queue sequence ordering. |
| Scope & Technical Goal | Build the backend virtual queue engine. When an appointment transitions to CHECKED_IN, assign an incremental daily queue token (e.g. A-01, B-04). Implement state machine endpoints (POST /api/queue/call-next, POST /api/queue/advance, POST /api/queue/no-show) ensuring non-colliding tokens and strict FIFO ordering per room. |
| Dependencies & Deadline | Blocked by: None (Booking engine Done!) • Blocks: [FE] Queue Screen & [FS] Staff Room View • Target: Monday, 14 Sep 2026, 5:00 PM |
| Acceptance Criteria | • Generates non-colliding daily sequence tokens reset at 00:00 UTC. • Enforces strict status transitions: BOOKED → CHECKED_IN → WAITING → CALLED → COMPLETED / NO_SHOW. • Calculates dynamic estimated wait time: (Remaining patients ahead) × (average consult duration 15 min). • GET /api/appointments/:reference/queue-status returns real-time position, estimated wait, and room token. |

| [BE] Appointment Cancellation & Slot Release API (Double-Release Prevention) |  |
| --- | --- |
| Status & Milestone | Active — High Priority ¦ Week 3 (Gate 3 Feature-Complete) |
| Assignee & Support | Primary: Able Kafu Azanda (AA) • Support: Emmanuella Lodonu |
| Assignment Rationale | Requires deep knowledge of Mongoose model hooks and compound indexes to ensure cancelled slots immediately re-open for booking. |
| Scope & Technical Goal | Develop PATCH /api/appointments/:id/cancel and PATCH /api/appointments/:id/reschedule. When an appointment is cancelled, update status to CANCELLED, release TimeSlot (isBooked: false, appointmentId: null), and make the slot immediately visible to other students in real time. |
| Dependencies & Deadline | Blocked by: None • Blocks: [FE] Self-Service Cancellation & Reschedule • Target: Tuesday, 15 Sep 2026, 5:00 PM |
| Acceptance Criteria | • Atomic slot release: Cancelling frees the slot, allowing another patient to immediately re-book it. • State validation: Cannot cancel an appointment already marked CHECKED_IN, CALLED, or COMPLETED. • Reschedule performs atomic swap (releases old slot and reserves new slot in a single operation). • Emits audit log stamp with cancelledTime and optional cancelReason. |

| [FE] Virtual Queue Live Status & Progress Screen (P18) |  |
| --- | --- |
| Status & Milestone | Active — High Priority ¦ Week 3 (Gate 3 Feature-Complete) |
| Assignee & Support | Primary: Raymond B. Afrani (RA) • Support: Harry “Ephraim” Nartey |
| Assignment Rationale | Direct continuation of Raymond's patient-facing frontend wizard, connecting the booking flow to live clinic queue monitoring. |
| Scope & Technical Goal | Implement Screen P18 (/queue) allowing checked-in patients to enter their Reference Code (YC-XXXX) or Phone to view their live token position (e.g. YC-014), estimated wait time in minutes, currently serving token, and real-time status banners ('You are 3rd in line', 'Proceed to Consultation Room 1'). Include auto-polling every 15 seconds. |
| Dependencies & Deadline | Blocked by: [BE] Virtual Queue Engine (Able) • Blocks: End-to-end patient queue tracking • Target: Wednesday, 16 Sep 2026, 5:00 PM |
| Acceptance Criteria | • Renders active patient token, queue depth, and calculated wait time based on clinic velocity. • Displays dynamic status transitions: CHECKED_IN → WAITING → CALLED → IN_CONSULTATION. • Visual pulsing banner and alert triggered when status updates to CALLED with room assignment. • Auto-polls /api/appointments/:id/queue-status every 15 seconds with graceful network retry. |

| [FE] Self-Service Cancellation & Rescheduling Flow (P11–P17) |  |
| --- | --- |
| Status & Milestone | Active ¦ Week 3 (Gate 3 Feature-Complete) |
| Assignee & Support | Primary: Raymond B. Afrani (RA) • Support: Harry “Ephraim” Nartey |
| Assignment Rationale | Completes the patient self-service lifecycle on the frontend, allowing students to manage their appointments without calling the clinic. |
| Scope & Technical Goal | Implement Screen P11 (Appointment Lookup & Details), P12 (Cancellation Confirmation dialog), P13 (Cancellation Complete), and P14–P17 (Reschedule calendar and slot picker). Allow students to enter their Reference Code + Phone to retrieve booking, cancel it with two-step confirmation, or select a new available date/time. |
| Dependencies & Deadline | Blocked by: [BE] Cancellation API (Able) • Blocks: Full patient self-service • Target: Thursday, 17 Sep 2026, 5:00 PM |
| Acceptance Criteria | • Students can look up booking using 6-character reference code (YC-XXXX) and verified phone number. • Cancel action displays modal confirmation preventing accidental cancellations. • Reschedule flow reuses the date/time picker, displaying only available future slots. • Displays clear cancellation/reschedule confirmation screen and notes that an SMS confirmation was sent. |

| [FS] Staff Multi-Room Consultation & Call-Next Workflow (S04/S05) |  |
| --- | --- |
| Status & Milestone | Active — High Priority ¦ Week 3 (Gate 3 Feature-Complete) |
| Assignee & Support | Primary: Harry “Ephraim” Nartey (HN) • Support: Able Kafu Azanda |
| Assignment Rationale | Harry established the staff portal foundation in Week 2 and has demonstrated fullstack capability across operational dashboards. |
| Scope & Technical Goal | Build the Doctor/Clinician consultation workstation view (S04/S05) on the Staff Portal. A clinician selects their active examination room (Room 1, Room 2, GF7), views the list of waiting patients for their site, clicks 'Call Next Patient', and completes the visit with clinical disposition notes (Completed, Follow-up Required, Referred). |
| Dependencies & Deadline | Blocked by: [BE] Virtual Queue Engine (Able) • Blocks: Clinical consultation cycle • Target: Wednesday, 16 Sep 2026, 5:00 PM |
| Acceptance Criteria | • Clinician can select and bind session to specific examination room. • 'Call Next Patient' button atomically transitions the next waiting appointment to CALLED and assigns token to room. • Action buttons: 'Start Consultation' (IN_CONSULTATION), 'Complete Visit' (COMPLETED), and 'Mark No-Show' (NO_SHOW). • Includes elapsed consultation timer and summary counter of patients seen today. |

| [FS] Walk-In Patient Fast-Track Intake & Desk Triage (S01/S02) |  |
| --- | --- |
| Status & Milestone | Active ¦ Week 3 (Gate 3 Feature-Complete) |
| Assignee & Support | Primary: Harry “Ephraim” Nartey (HN) • Support: Emmanuella Lodonu |
| Assignment Rationale | Essential operational requirement for clinic receptionists handling unscheduled emergency and walk-in students arriving directly at the clinic. |
| Scope & Technical Goal | Build the Receptionist Walk-In creation modal on /staff. Allows reception staff to quickly register an unscheduled student (or lookup existing record via index number or Ghana phone) and directly insert them into the day's active virtual queue as a walk-in visit without booking an online time slot. |
| Dependencies & Deadline | Blocked by: [BE] Patient Registration API (Done!) • Blocks: Hybrid online/walk-in queue • Target: Thursday, 17 Sep 2026, 5:00 PM |
| Acceptance Criteria | • Modal fields: Student Index, Full Name, Phone, Visit Type, and Triage Priority (Standard vs Urgent). • Creates patient (if new) and immediately inserts appointment with bookingType: 'WALK_IN' and status: 'CHECKED_IN'. • Assigns walk-in sequence token (e.g. W-024) placed appropriately in the queue. • Immediate visual feedback on the staff queue roster with zero page reload. |

| [BE] Call-Next Patient SMS Notification Dispatch |  |
| --- | --- |
| Status & Milestone | Active ¦ Week 3 (Gate 3 Feature-Complete) |
| Assignee & Support | Primary: Emmanuella Lodonu (EL) • Support: Blessing Edmund Kwame Dogbe (Lead) |
| Assignment Rationale | Emmanuella owns the SMS integration triggers in the backend and verified mNotify gateway delivery during Gate 2. |
| Scope & Technical Goal | Hook the SMS service to the 'Call Next' queue transition event. When a clinician calls a patient, automatically send an immediate alert SMS: 'YenCare: Token [Token] is now called to Consulting Room [Room]. Please proceed inside immediately.' Ensure rapid delivery so students waiting in nearby corridors or hostels do not miss their turn. |
| Dependencies & Deadline | Blocked by: [BE] Queue Engine & [FS] Staff Room View • Blocks: Gate 3 notification loop • Target: Wednesday, 16 Sep 2026, 5:00 PM |
| Acceptance Criteria | • SMS triggers automatically upon appointment transitioning to CALLED. • Message template concise (<140 characters) and pre-tested with Ghana network delivery. • Logs delivery latency and mNotify message ID. • Non-blocking: SMS network delay does not delay the doctor's UI response. |

| [DEVOPS] Multi-Container Staging & Cloud Database Autoscaling |  |
| --- | --- |
| Status & Milestone | Active ¦ Week 3 (Gate 3 Feature-Complete) |
| Assignee & Support | Primary: Blessing Edmund Kwame Dogbe (DevOps / Lead) • Support: Team Lead Self-Directed |
| Assignment Rationale | Blessing's DevOps domain ensures infrastructure is robust enough to handle simultaneous staff and student connections during multi-client evaluation. |
| Scope & Technical Goal | Upgrade the cloud staging environment on Render/Railway. Deploy both the frontend React client and the Express backend as connected services with environment synchronization. Configure automated database backups on MongoDB Atlas, connection pooling (min 10, max 50 pool size), and CORS policies restricted to staging domains. |
| Dependencies & Deadline | Blocked by: Week 2 Staging Setup (Done!) • Blocks: Gate 3 multi-user evaluation • Target: Thursday, 17 Sep 2026, 5:00 PM |
| Acceptance Criteria | • Frontend and backend communicate seamlessly on public HTTPS staging URLs. • MongoDB connection pooling configured to prevent socket starvation under multi-client load. • Automated nightly snapshot backups enabled on MongoDB Atlas cluster. • Healthcheck endpoint /health monitors database connection state and response latency. |

| [LEAD] Gate 3 Feature-Freeze Verification & Submission |  |
| --- | --- |
| Status & Milestone | Active — Programme Milestone ¦ Week 3 (Official Gate 3 Milestone) |
| Assignee & Support | Primary: Blessing Edmund Kwame Dogbe (DevOps / Lead) • Support: AmaliTech Programme Coordinators |
| Assignment Rationale | Official programme milestone submission, governance, and feature-freeze enforcement. |
| Scope & Technical Goal | Execute the comprehensive Gate 3 feature review: verify that patient booking, SMS alerts, virtual queue tracking, staff consultations, walk-in triage, and cancellations are 100% operational. Enforce the strict code freeze on the repository main branch at 5:00 PM on Friday, 18 September. Submit the Gate 3 Progress Assessment to AmaliTech coordinators. |
| Dependencies & Deadline | Blocked by: All Week 3 deliverables • Blocks: Gate 3 approval and transition to Week 4 Hardening • Target: Friday, 18 Sep 2026, 5:00 PM |
| Acceptance Criteria | • End-to-end multi-role verification passed on staging (Patient + Receptionist + Doctor). • Branch protection enabled on main: feature freeze enacted, only bugfix PRs accepted. • AmaliTech Gate 3 Submission Form completed with architecture diagrams and live staging URL. • Sprint retrospective and Week 4 hardening kickoff meeting scheduled. |

# 5. Week 3 Team Synchronization & Pairing Schedule

To ensure on-time delivery before the strict Friday 5:00 PM feature freeze, the team will adhere to the following daily execution rhythm:

| Day & Time | Event / Milestone | Key Objectives & Participants |
| --- | --- | --- |
| Monday, 14 Sep 10:00 AM | Week 3 Sprint Kickoff | Align on Gate 3 acceptance criteria. Able presents queue state machine API contract. Harry and Raymond align frontend payloads. |
| Tuesday, 15 Sep 5:00 PM | Backend Handover Checkpoint | Able delivers Virtual Queue Engine and Cancellation APIs. Emmanuella verifies SMS trigger payloads with mNotify sandbox. |
| Wednesday, 16 Sep 2:00 PM – 4:00 PM | Live Integration Work-Session | Mandatory pairing session: Harry connects doctor consultation room to queue endpoints; Raymond connects /queue live tracking. |
| Thursday, 17 Sep 4:00 PM | End-to-End Simulation Dry-Run | Full clinical workflow rehearsal: Patient books online → arrives & checks in → doctor calls next → SMS fires → walk-in triage added → booking cancelled. |
| Friday, 18 Sep 5:00 PM SHARP | Feature Freeze & Gate 3 Submission | Branch protection locked on main branch. Blessing submits AmaliTech Gate 3 Progress Assessment and demo recording. Feature freeze begins. |

# 6. Forward Delivery Plan: Week 4 Hardening & Week 5 Final Demo

Following the Gate 3 Feature Freeze at 5:00 PM on Friday, 18 September, Weeks 4 and 5 are strictly protected from new feature development. The team will focus exclusively on reliability, performance, clinical impact documentation, and executive presentation:

## Week 4: Gate 4 (Reviewed, Fixed & Documented — Target: Fri 25 Sep 2026)

| Deliverable / Task Title | Owner | Scope & Done Criteria |
| --- | --- | --- |
| [TEST] Concurrency Stress Testing & Profiling | Able Azanda | Execute load testing using k6 simulating 100 simultaneous requests/sec. Ensure p95 latency < 200ms and zero double-bookings occur. |
| [SEC] Data Protection, Phone Masking & Audit | Emmanuella Lodonu | Implement phone masking on public screens (+233 24 **** 567), sanitize inputs against NoSQL injection, and verify environment secrets. |
| [FE] Cross-Device Mobile Responsiveness & A11y | Raymond Afrani | Test screens across real mobile devices (Safari, Chrome, 3G throttled mode). Fix tap targets, padding, and contrast compliance. |
| [FS] Network Resilience & Offline Fallback UX | Harry Nartey | Implement toast banners and reconnect handling when clinic Wi-Fi drops. Ensure staff queue state persists during temporary blips. |
| [DOCS] Comprehensive Architecture Specs & Runbook | Blessing Dogbe | Author complete system documentation: API catalog, database schema, environment setup guides, and disaster recovery runbooks. |

## Week 5: Gate 5 (Demo Delivered + Insights Shared — Target: Fri 2 Oct 2026)

| Deliverable / Task Title | Owner | Scope & Done Criteria |
| --- | --- | --- |
| [DEMO] End-to-End Clinical Simulation Rehearsal | All Team Members | Conduct multi-role rehearsals simulating a full morning at KNUST Students' Clinic: 5 book online, 2 arrive as walk-ins, doctors call tokens, SMS fires. |
| [DATA] Clinical Impact Analysis & Wait-Time Modeling | Able & Emmanuella | Calculate simulated throughput improvements: model how virtual queuing and time slots reduce peak waiting room crowding by an estimated 65%. |
| [SLIDES] Executive Stakeholder Pitch Deck & Video | Raymond & Harry | Produce the final presentation slide deck, architecture diagrams, and a 3-minute high-definition product walkthrough video demonstrating the live system. |
| [LEAD] Final Capstone Defence & AmaliTech Handover | Blessing Dogbe | Lead final presentation to AmaliTech CSR evaluators and KNUST clinical stakeholders. Deliver final repository bundle and retrospective insights. |